## How to use
Production schedule template
From Moonb: moonb.io/templates/production-schedule-template
1. Set the start date.
On "Schedule", change the date in C3. Every task date moves with it, and the timeline redraws.
2. Make the tasks yours.
Rename, delete or add rows. Dates are formulas, so type over any of them when a real date is fixed.
3. Put the reviews in.
Review rounds are where schedules slip. Give each one an owner and a date, the same as the shoot.
4. Plan each shoot day.
Use the "Shoot day" tab for call times and setups. Duplicate it for every day you film.
5. Move the status every day of production.
Not started, in progress, waiting on feedback, done, blocked. Blocked rows turn red so they get seen.
Phase colors on the timeline
Pre-production
Production
Post-production
Delivery

## Schedule
Production schedule
Set the start date in C3. Dates are formulas you can overwrite; the timeline on the right colors itself by phase.
Start date |  | 2026-11-02 12:00 |  | Project
Phase | Task | Owner | Start | End | Days | Status | Notes
Pre-production | Brief signed off | Client |  |  |  | Not started
Pre-production | Script first draft | Writer |  |  |  | Not started
Pre-production | Script approved | Client |  |  |  | Not started
Pre-production | Storyboard and shot list | Director |  |  |  | Not started
Pre-production | Casting and talent releases | Producer |  |  |  | Not started
Pre-production | Locations, permits and insurance | Producer |  |  |  | Not started
Pre-production | Crew, kit and call sheet | Producer |  |  |  | Not started
Production | Shoot day 1 | Director |  |  |  | Not started
Production | Shoot day 2 | Director |  |  |  | Not started
Production | Footage backed up and logged | Editor |  |  |  | Not started
Post-production | First cut | Editor |  |  |  | Not started
Post-production | Review round 1 | Client |  |  |  | Not started
Post-production | Second cut | Editor |  |  |  | Not started
Post-production | Review round 2 | Client |  |  |  | Not started
Post-production | Color, sound mix and graphics | Editor |  |  |  | Not started
Post-production | Captions and cut-downs | Editor |  |  |  | Not started
Delivery | Final approval | Client |  |  |  | Not started
Delivery | Masters and versions delivered | Producer |  |  |  | Not started
Delivery | Files archived and handed over | Producer |  |  |  | Not started

## Shoot day
Shoot day plan
One tab per shoot day. Duplicate it for day two.
Date |  |  | Location
Producer on set |  |  | Weather backup
Time | What happens | Who | Where | Shots or scenes | Notes
07:30 | Crew call, kit check | Crew | Base
08:00 | Talent call, hair and makeup | Talent | Green room
08:30 | Light the first setup | Crew | Set A
09:00 | Shoot setup 1 | All | Set A | 1 to 4
11:00 | Shoot setup 2 | All | Set B | 5 to 9
13:00 | Lunch | All |  |  | One hour, not negotiable
14:00 | Shoot setup 3 | All | Set C | 10 to 14
16:30 | Pickups and cutaways | Camera | Around site | B-roll list
17:30 | Wrap, back up footage | Crew | Base |  | Two copies before anyone leaves

## Lists
Phases | Statuses | Owners
Pre-production | Not started | Producer
Production | In progress | Director
Post-production | Waiting on feedback | Writer
Delivery | Done | Editor
| Blocked | Client
Add names here