# Project brief

One document that says why the project exists, what is in and out, who decides and when it is done. Agree it before kickoff and the arguments happen on paper, not halfway through.

| Project name |  | Project owner |  | Start date |  | Deadline |
| --- | --- | --- | --- | --- | --- | --- |

Inside

| 01 | Background | 2 |  | 08 | Budget and resources | 4 |
| --- | --- | --- | --- | --- | --- | --- |
| 02 | The goal | 2 |  | 09 | Risks and dependencies | 4 |
| 03 | How we will know it worked | 2 |  | 10 | How we keep in touch | 4 |
| 04 | Scope | 2 |  | 11 | Approval | 4 |
| 05 | Deliverables | 3 |  |  | Worked example | 5 |
| 06 | Milestones | 3 |  |  | Before kickoff | 6 |
| 07 | Who is involved | 3 |  |  | Project brief or creative brief? | 6 |

Click into any box and type. Boxes grow to fit what you write. Send it to everyone on the stakeholder list and get the approval on the last form page before work starts.

## 01 Background

Why this project, and why now. Two or three sentences a new team member could read and understand.

## 02 The goal

One sentence. If you need two, you probably have two projects.

## 03 How we will know it worked

Numbers you can check after launch, with where they are today. A target without a starting point cannot be judged. What we measure; Today; Target; By when.

## 04 Scope

Out of scope matters as much as in. Writing it down is how you stop the project growing a little every week. In scope; Out of scope.

## 05 Deliverables

Every thing that gets handed over, with its format, one owner and a date. Deliverable; Format or spec; Owner; Due.

## 06 Milestones

The points where work stops for a decision. Put a date under each, then work back from the deadline. ● Kickoff Date; ● First draft Date; ● Review Date; ● Final sign-off Date; ● Launch Date.

## 07 Who is involved

Name the one person who approves. Everyone else either works on it, gets asked, or gets told. Name; Role on this project; Approves, works on, asked or told; Contact.

## 08 Budget and resources

The money, the people and the tools. Say if the budget is fixed or if there is room for a change request. Budget; People and time; Tools and access.

## 09 Risks and dependencies

What could stop or slow this down, and what you will do about it. Include anything you are waiting on from another team. Risk or dependency; How likely; What we will do.

## 10 How we keep in touch

How often the team reports progress, where, and where the files and decisions live, so nobody has to ask. Status updates (how often, where, who); Where files and decisions live.

## 11 Approval

Signed before work starts. Changes to the goal, scope or deadline after this point go through a short change note. Approved by; Role; Date; Signature.

Worked example

# A filled project brief for a website redesign

Illustrative. A software company rebuilding its marketing site in one quarter.

| 02 The goal. Launch a new marketing site by March 31 that turns more visits into demo requests... |  | One sentence with a deadline. Every scope question gets checked against it. |
| --- | --- | --- |
| 03 How we will know it worked. What we measure; Today; Target; By when. Visits that request a demo; 0.8%; 1.5%; 60 days after launch. Pages that load in under 2.5 seconds; 40%; 90%; At launch.. |  | Each target has a starting point, so the result can be judged honestly. |
| 04 Scope. In: home page, product pages, pricing, about, careers, the demo form, new templates the team can edit without a developer.; Out: the blog (moves as is), the help center, translations, a new logo... |  | The blog and the help center are named as out, so nobody adds them in week six. |
| 06 Milestones. Milestone; Date; Decision. Kickoff; Jan 6; Brief signed, team confirmed. First draft; Jan 31; Page plan and design direction. Review; Feb 21; Every page built, content in. Final sign-off; Mar 14; Approved for launch. Launch; Mar 31; Live, old site redirected.. |  | Each date is a decision, not just a reminder. |

# Before kickoff

Seven checks. If one is missing, the project usually pays for it later.

|  | The goal fits in one sentence. And everyone on the stakeholder list would describe it the same way. |
| --- | --- |
|  | Every target has a starting number. Find it now. After launch nobody will remember what it was. |
|  | Out of scope is written down. At least three things people might reasonably expect, named as out. |
|  | One person approves. A group can give input. Only one name signs off. |
|  | Every deliverable has one owner and a date. Two owners means nobody owns it. |
|  | Risks have an action next to them. A risk with no plan is just a worry. |
|  | It is signed before work starts. Changes after that go through a short change note, not a hallway chat. |

# Project brief or creative brief?

They work together. The project brief runs the project; a creative brief briefs the work inside it.

|  | Project brief | Creative brief |
| --- | --- | --- |
| Answers | Why, what, who, when and how much | What the work must say and to whom |
| Written by | The project owner | The marketer or account lead |
| Read by | Everyone involved, including finance and legal | The designers, writers and filmmakers |
| Covers | Scope, deliverables, milestones, budget, risks | Audience, message, tone, mandatories |
| Changes when | Scope, budget or deadline change | The message or audience changes |